Phase 4 — Project Planning

Planning Logic

Development planning and task breakdown for DocSpot

DocSpot: Seamless Appointment Booking for Health

Project Documentation  |  2024

# 1. Project Planning Approach

DocSpot uses an agile-inspired iterative development approach with clearly defined sprints. Each sprint targets a specific functional area of the platform, ensuring incremental delivery and continuous testing.

## 1.1 Development Sprints

| Sprint | Focus Area | Duration | Status |
| --- | --- | --- | --- |
| Sprint 1 | Project setup, folder structure, environment config | 2 days | Complete |
| Sprint 2 | Backend schemas, MongoDB connection, Express server | 2 days | Complete |
| Sprint 3 | User authentication (register, login, JWT, middleware) | 2 days | Complete |
| Sprint 4 | Doctor application and admin approval workflow | 3 days | Complete |
| Sprint 5 | Appointment booking with file upload | 3 days | Complete |
| Sprint 6 | Notification system (create, mark seen, delete) | 2 days | Complete |
| Sprint 7 | React frontend setup, routing, layout component | 2 days | Complete |
| Sprint 8 | Auth pages: Login, Register, Home landing page | 2 days | Complete |
| Sprint 9 | User dashboard: Doctor list, Booking modal | 3 days | Complete |
| Sprint 10 | Admin dashboard: Users, Doctors, Appointments | 3 days | Complete |
| Sprint 11 | Testing, bug fixes, UI polish | 2 days | Complete |

# 2. Task Breakdown

## 2.1 Backend Tasks

| Task ID | Task | Complexity | Dependencies |
| --- | --- | --- | --- |
| BE-1 | Setup Express server with CORS and body-parser | Low | None |
| BE-2 | Connect MongoDB using Mongoose | Low | BE-1 |
| BE-3 | Create User, Doctor, Appointment schemas | Medium | BE-2 |
| BE-4 | Implement user registration with bcrypt hashing | Medium | BE-3 |
| BE-5 | Implement login with JWT token generation | Medium | BE-4 |
| BE-6 | Create JWT auth middleware | Low | BE-5 |
| BE-7 | Doctor application controller and route | Medium | BE-6 |
| BE-8 | Admin approve/reject doctor controller | Medium | BE-7 |
| BE-9 | Appointment booking with Multer file upload | High | BE-8 |
| BE-10 | Notification system (push and mark seen) | Medium | BE-9 |
| BE-11 | Doctor profile update controller | Low | BE-10 |
| BE-12 | Admin user management (list, delete) | Low | BE-6 |

## 2.2 Frontend Tasks

| Task ID | Task | Complexity | Dependencies |
| --- | --- | --- | --- |
| FE-1 | Create React app, install dependencies | Low | None |
| FE-2 | Setup React Router with protected routes | Medium | FE-1 |
| FE-3 | Build Layout component with sidebar | Medium | FE-2 |
| FE-4 | Build Home landing page | Low | FE-2 |
| FE-5 | Build Login and Register forms with API integration | Medium | FE-3, BE-5 |
| FE-6 | Build User Home with doctor cards | Medium | FE-3, BE-7 |
| FE-7 | Build Booking Modal with datetime and file upload | High | FE-6, BE-9 |
| FE-8 | Build My Appointments page with cancel feature | Medium | FE-3, BE-9 |
| FE-9 | Build Apply Doctor form | Medium | FE-3, BE-7 |
| FE-10 | Build Notifications page | Medium | FE-3, BE-10 |
| FE-11 | Build Admin Home with stats and appointments table | Medium | FE-3, BE-12 |
| FE-12 | Build Admin Doctors page with approve/reject | Medium | FE-3, BE-8 |
| FE-13 | Build Admin Users page with search and delete | Medium | FE-3, BE-12 |
| FE-14 | CSS polish, responsive design, accessibility | Medium | All FE tasks |

# 3. Risk Assessment

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| JWT token expiry causing session issues | Medium | High | Handle 401 errors and redirect to login |
| MongoDB connection failure | Low | High | Error handling in connectToDB.js with process.exit |
| File upload exceeding server storage | Low | Medium | 5MB limit enforced via Multer configuration |
| CORS blocking API calls in production | Medium | High | Configure CORS origins for production environment |
| Scope creep adding unplanned features | Medium | Medium | Stick to MVP feature list, defer extras to Phase 2 |
| Inconsistent state after notifications update | Low | Medium | Re-fetch user data after notification mutations |